## Slide 1
Standards & Qualifications for Guests of Allah Program
Prepared by Impetus Strategy Impetus Strategy

## Slide 2
Agenda
Introduction & Overview
RFP Understanding & Objectives
Approach & Methodology
Work Plan & 15-Day Timeline
Team & Resources
Deliverables & KPIs
2

## Slide 3
Agenda
Quality & Risk Management
Pricing & Payment
Compliance & Data Governance
Why Impetus Strategy
Thank You
3

## Slide 4
Introduction & Overview

## Slide 5
Company Introduction
6
Develop functional standards and job descriptions for 10 priority roles serving Guests of Allah with alignment to Saudi occupational classification
Map, design, and register 10 corresponding qualifications under SAQF with outcome-based structures and compliant assessment strategies
Design and implement training programs for 1,000 candidates with provider criteria, curricula, awareness packages, and LMS-ready materials
Define incentives and enablers that increase nonprofit participation, embed monitoring, quality management, risk controls, and formal closeout

## Slide 6
RFP Understanding & Objectives

## Slide 7
RFP Objectives
Develop functional standards and job descriptions for 10 priority roles serving Guests of Allah with alignment to Saudi occupational classification
Map, design, and register 10 corresponding qualifications under SAQF with outcome-based structures and compliant assessment strategies
Design and implement training programs for 1,000 candidates with provider criteria, curricula, awareness packages, and LMS-ready materials
Define incentives and enablers that increase nonprofit participation, embed monitoring, quality management, risk controls, and formal closeout
8

## Slide 8
Approach & Methodology

## Slide 9
Framework Overview
Standards engineering combining occupational analysis, competency modeling, and qualification blueprinting to codify role requirements and performance
SAQF alignment with outcome-based design, assessment strategies, progression pathways, and full registration protocol compliance
Workforce enablement via training pathways, provider qualification criteria, contracting model, and operating model for scaled execution
Impact enablement through incentives and enablers mapped to stakeholder economics, feasibility assessments, and policy alignment within PMO governance
10

## Slide 10
Phased Methodology
Phases 1–2 Planning and Mobilization, then Job Analysis and Role Descriptions including beneficiary journey review, functional task analysis, and benchmarking
Phase 3 SAQF Qualification Design and Registration covering purpose, outcomes, structure, assessment, progression, consultations, and formal submission
Phases 4–5 Training Programs Execution plus Incentives and Enablers including provider selection, curricula, 10 training and 10 awareness e-packages, and campaigns
Phases 6–7 Monitoring and Control with weekly tracking, KPI dashboard, quality reviews, risk refresh, followed by closure and knowledge handover
11

## Slide 11
Methodological Pillars
Evidence-based design using surveys, focus groups, and benchmarks
SAQF-compliant learning outcomes and assessment alignment
Human-centered excellence for pilgrim and visitor journeys
Governance, transparency, and local content adherence
12

## Slide 12
Work Plan & 15-Day Timeline

## Slide 13
15-Day Mobilization Timeline
Day | Activity | Key Outputs | Dependencies | Owner
1 | Kickoff and governance setup | Approved charter, RACI, communication plan | Contract signature | EPMO Manager
2 | PMO templates alignment | Adopted meeting minutes, risk register, lessons learned templates | Client PMO inputs | EPMO Manager
3 | Stakeholder mapping | Stakeholder register, engagement cadence | Kickoff complete | Managing Director
14

## Slide 14
15-Day Mobilization Timeline
Day | Activity | Key Outputs | Dependencies | Owner
4 | Detailed work breakdown (WBS) | Phase-wise WBS, deliverable acceptance criteria | Governance setup | Engagement Manager
5 | Quality plan and QA checklists | QA plan covering all deliverables | WBS finalization | Quality Lead
6 | Risk assessment workshop | Initial risk log with mitigations | Stakeholder mapping | EPMO Manager
15

## Slide 15
15-Day Mobilization Timeline
Day | Activity | Key Outputs | Dependencies | Owner
7 | Data request and access plan | Data inventory and access schedule | PMO alignment | Data Lead
8 | Beneficiary journey review prep | Interview guides, FGD guides, survey drafts | Data access plan | Standards Lead
9 | Provider criteria draft | Draft selection criteria for training providers | WBS/QA alignment | Training Lead
16

## Slide 16
15-Day Mobilization Timeline
Day | Activity | Key Outputs | Dependencies | Owner
10 | SAQF registration blueprint | Templates for outcomes, assessment, progression | Standards framework | Educational Expert
11 | KPI and M&E framework | Draft KPIs for role impact and training | QA plan | M&E Lead
12 | Incentives/enablers framework | Option catalog and evaluation criteria | Stakeholder register | Policy Lead
17

## Slide 17
15-Day Mobilization Timeline
Day | Activity | Key Outputs | Dependencies | Owner
13 | MS Project baseline schedule | Baselined plan; critical path and milestones | WBS complete | EPMO Manager
14 | Communication & reporting plan | Weekly/quarterly reporting formats | PMO templates | EPMO Manager
15 | Mobilization closeout review | Approved Mobilization Pack; go/no-go for Phase 2 | All prior outputs | Steering Committee
18

## Slide 18
Project Timeline by Phase
Chart: Phase Duration
| Phase 1 — Planning & Mobilization | Phase 2 — Job Analysis & Descriptions | Phase 3 — SAQF Design & Registration | Phase 4 — Training Programs Execution | Phase 5 — Incentives & Enablers | Phase 6 — Monitoring & Control | Phase 7 — Closure
Duration (Weeks) | 2 | 5 | 5 | 8 | 3 | 12 | 1
19

## Slide 19
Project Phases & Timeline
Phase | Key Activities | Duration | Key Outputs
Planning & Mobilization | Charter, governance, RACI, PMO alignment, baseline schedule | 2 weeks | Mobilization & Inception Pack
Analysis & Role Design | Beneficiary journey review, task analysis, focus groups, benchmarking | 5 weeks | 10 Job Description Cards
SAQF Registration | Outcomes, structure, assessment, consultations, submissions | 5 weeks | 10 SAQF Qualifications Registered
20

## Slide 20
Project Phases & Timeline
Phase | Key Activities | Duration | Key Outputs
Training Execution | Provider contracting, curricula, 10 training and 10 awareness e-packages | 8 weeks | 1,000 Candidates Trained with reports
Closure & Handover | Final acceptance, lessons learned, archival, closeout | 1 week | Final Report and Handover
21

## Slide 21
Team & Resources

## Slide 22
Team Structure & Responsibilities
Position | Responsibilities | Experience | Time Allocation
Managing Director | Executive sponsor, stakeholder alignment, quality oversight | 15+ years | 20%
EPMO Manager | PMO governance, schedule, risks, reporting, budget control | 12+ years | 40%
Engagement Manager | Lead phases 2–5, standards, SAQF, training ops, incentives design | 10+ years | 60%
23

## Slide 23
Team Structure & Responsibilities
Position | Responsibilities | Experience | Time Allocation
Global Projects Lead | Complex program integration, benefits realization, benchmarking | 14+ years | 25%
Educational Expert | Qualification design, outcome-based assessment, accreditation | 12+ years | 35%
Standards Consultant | Competency modeling, training package architecture | 8+ years | 50%
24

## Slide 24
Team Structure & Responsibilities
Position | Responsibilities | Experience | Time Allocation
Training Coordinator | Provider liaison, cohort scheduling, logistics, reporting | 7+ years | 70%
25

## Slide 25
Tools, Systems & Architecture
MS Project for scheduling and critical path management with weekly updates and baseline control
Productivity suite for authoring and design including Word, PowerPoint, and PDF templates aligned to PMO standards
Data analysis and survey tools specified by PMO with validated collection, cleaning, and reporting workflows
Client platforms for archival and reporting with e-archiving, version control, and least-privilege access
26

## Slide 26
Deliverables & KPIs

## Slide 27
Project Deliverables
Deliverable | Description | Timeline | Format
Mobilization & Inception Pack | Charter, governance, RACI, PMO templates, baseline schedule | Week 2 | PDF + XLS + MS Project
Job Standards Portfolio | Classified roles and 10 job description cards with competencies and SAQF domains | Week 8 | Bound Report + Cards
SAQF Qualification Dossier | 10 qualifications with outcomes, structure, assessment, and registrations | Week 14 | SAQF Forms + Evidence Set
28

## Slide 28
Project Deliverables
Deliverable | Description | Timeline | Format
Training Delivery Portfolio | Criteria, contracts, curricula, 10 training, 10 awareness, 10 e-packages for 1,000 candidates | Week 24 | Documents + LMS Packages
Incentives & Final Handover | Incentives roadmap, campaigns, KPI guide, archival upload, final report and acceptance | Week 26 | Report + Playbooks + Presentation
29

## Slide 29
Key Performance Indicators
KPI | Target | Measurement Method | Frequency
Standards First-Submission Acceptance | ≥90% | Quality review against acceptance criteria | Per deliverable
SAQF Registration Completion | 100% of 10 | SAQF acceptance records | Per qualification
Training Completion Rate | ≥90% | Attendance and completion tracking | Per cohort
30

## Slide 30
Key Performance Indicators
KPI | Target | Measurement Method | Frequency
Trainee Satisfaction | ≥85% | Post-training surveys | Per cohort
Assessment Pass Rate | ≥70% | Assessment results and verification | Per cohort
31

## Slide 31
Performance Metrics Targets
Chart: Key Performance Indicators
| Standards Acceptance | SAQF Registrations | Training Completion | Trainee Satisfaction | Assessment Pass Rate | On-time Deliverables
Target | 90 | 100 | 90 | 85 | 70 | 95
32

## Slide 32
Quality & Risk Management

## Slide 33
Quality, Risks, and Change Control
Quality management with defined acceptance criteria per deliverable, peer reviews, SAQF and occupational classification conformance, and semiannual QA reports
Risk controls addressing data availability, stakeholder scheduling, SAQF timelines, provider readiness, and policy dependencies with mitigations and staged approvals
Monitoring cadence with weekly tracking, KPI dashboard, MS Project updates, and quality conformance reviews at agreed intervals
Formal change control via PMO with impact assessment across scope, time, cost, and quality before approval and implementation
34

## Slide 34
Pricing & Payment

## Slide 35
Payment Schedule
Phase | Milestone | Payment % | Timeline
Mobilization | Contract signing, inception pack approved | 15% | Week 2
Standards Delivery | 10 job descriptions approved | 20% | Week 8
SAQF Registration | 10 qualifications registered | 25% | Week 14
36

## Slide 36
Payment Schedule
Phase | Milestone | Payment % | Timeline
Training Execution | Cohorts delivered and interim reports accepted | 25% | Weeks 16–24
Incentives & Closure | Incentives package, final report, acceptance | 15% | Week 26
37

## Slide 37
Budget Allocation by Workstream
Chart: Cost Distribution
| Standards & Job Descriptions | SAQF Registration | Training Programs | Incentives & Campaigns | PMO & QA
Percentage | 20 | 20 | 45 | 10 | 5
38

## Slide 38
Compliance & Data Governance

## Slide 39
Data Privacy, Security, and Compliance
Confidentiality aligned to RFP with no public disclosure without prior written consent and controlled information sharing channels
Data handling via client-approved systems with least-privilege access and archival on the program’s e-archiving platform for traceability
IP ownership of proposal content and resulting deliverables resides with the client with reuse only by explicit written permission
RFP compliance on Arabic delivery, PMO templates, ethics, conflict of interest, localization, guarantees, and submission formatting
40

## Slide 40
Why Impetus Strategy

## Slide 41
Relevant Experience & Case Evidence
National social and economic surveys delivering large-scale data and policy insights across priority regions with multi-phase execution
Guests of Allah functional standards and qualification work combined with workforce training enablement and volunteer incentive frameworks
Visitor and resident experience measurement in Makkah including JLL collaboration with frameworks for iterative improvement
Social investment strategy and nonprofit strategy development including Hadyiah and SAKAN housing product design
42

## Slide 42
Our Value Proposition
Integrated methodology spanning standards, SAQF, training, and incentives
PMO-first governance with rigorous QA and measurable KPIs
Localized impact-driven team with rapid mobilization capability
Proven delivery on Guests of Allah initiatives at scale
43

## Slide 43
Thank You

## Slide 44
Next Steps
Schedule a technical deep dive on standards engineering, SAQF registration workflow, and training operating model
Confirm governance contacts, reporting cadence, and PMO templates to align mobilization and decision gates
Kick off 15-day mobilization to deliver the approved Mobilization Pack and go or no-go for Phase 2
Agree on stakeholder access windows, data requests, and workshop logistics for phases 2–4
45