## Slide 1
Building Functional Standards and Workforce Qualification for the Guests of Allah Program
Proposal — Prepared by Impetus Strategy Impetus Strategy

## Slide 2
Agenda
Executive Summary
RFP Understanding & Objectives
Technical Approach & Methodology
Project Architecture & Technology
Relevant Experience
Project Team
2

## Slide 3
Agenda
Compliance with RFP
Deliverables Summary
Assumptions & Pricing
Why Impetus Strategy
3

## Slide 4
Executive Summary
• End-to-end engagement across 7 phases
  ○ Planning to closure with robust governance
  ○ Direct mirror of RFP scope and outcomes
• Ten prioritized roles and SAQF-aligned standards
  ○ JD cards with competency models and learning domains
  ○ Qualification specifications mapped to SAQF
• Ten qualifications registered on SAQF
  ○ Stakeholder participation and evidence-based submissions
  ○ Iterative review and approvals management
4

## Slide 5
Executive Summary
• Upskilling at scale: 1,000 candidates
  ○ Content, delivery partnerships, and PMO
  ○ Curricula and e-learning packages
• Incentives and enablers portfolio
  ○ Awareness campaigns with implementation roadmaps
  ○ Practical levers to boost sector participation
• Quality, risk, and knowledge transfer
  ○ Weekly reporting and milestone reviews
  ○ Capacity building for client teams
5

## Slide 6
Company Introduction
• Strategy and impact consulting across priority sectors
  ○ Public sector and third sector transformation
  ○ Education, skills, social and economic development
• Measurable impact beyond profitability
  ○ Operating models, policies, and impact investment
  ○ Large-scale capability-building programs
• Capabilities portfolio
  ○ Strategy, governance, and ecosystem design
  ○ Impact, sustainability, digital social development
• Stakeholder enablement and investment
  ○ Service enablement and engagement
  ○ Impact investment strategies
• Global partnerships and knowledge networks
  ○ Advanced methodologies
  ○ Deep sector insights
6

## Slide 7
Understanding of the RFP and Objectives
• Analyze and define 10 priority roles
  ○ Non-profit ecosystem serving pilgrims and Umrah
  ○ Role clarity and minimum requirements
• Specify education, experience, and competencies
  ○ Behavioral and technical
  ○ Leadership and role levels
• Design and register 10 SAQF-aligned qualifications
  ○ Learning outcomes, levels, progression
  ○ Assessment strategies
• Deliver programs to 1,000 candidates
  ○ Strong governance and reporting
  ○ Localization and quality assurance
• Establish incentives and enablers
  ○ Boost workforce participation and impact
  ○ Compliance with Saudi regulations
7

## Slide 8
Critical Success Factors (from RFP)
• Transparent and equitable processes
  ○ Confidentiality and fairness
• Robust governance, risk, and QA
  ○ Clear acceptance criteria and reviews
• Local content and workforce
  ○ Arabic-first materials and Saudization
• Methodology and workplan strength
  ○ Meets evaluation criteria
  ○ Demonstrated relevant experience
8

## Slide 9
Technical Approach & Methodology
9

## Slide 10
Framework Overview
• Policy-to-Operations alignment
  ○ Vision 2030, program objectives, regulations
  ○ Mapped to role standards and delivery
• Competency and Qualification design
  ○ Job architecture and models
  ○ SAQF-compliant blueprints and assessments
• Delivery and Impact engine
  ○ Training pathways and partner enablement
  ○ Program management and incentives activation
10

## Slide 11
Phased Methodology (Phases 1–3)
• Phase 1: Planning & Mobilization
  ○ Charter, governance, acceptance criteria
  ○ MS Project plan, risk & quality, KM setup
• Phase 2: Job Analysis & Role Descriptions
  ○ Journey review, role inventory, surveys/FGDs
  ○ 10 JDs per Saudi Classification of Occupations
• Phase 3: SAQF Alignment
  ○ Purpose, structure, outcomes, assessment
  ○ Register 10 qualifications; manage reviews
11

## Slide 12
Phased Methodology (Phases 4–7)
• Phase 4: Qualification Program Delivery
  ○ Provider criteria, partnership framework
  ○ ILPs, ops & logistics for 1,000; ≥5 reports
• Phase 5: Incentives & Enablers
  ○ Diagnose, analyze interfaces, enabling levers
  ○ Portfolio, roadmap, 3 campaigns, measure impact
• Phase 6: Monitoring & Control
  ○ Weekly tracking & dashboards
  ○ Semi-annual QA and risk log updates
• Phase 7: Closure
  ○ Final acceptance and lessons learned
  ○ Knowledge transfer and close-out docs
12

## Slide 13
Methodological Pillars
• Evidence-based design
  ○ Surveys, FGDs, interviews
  ○ Benchmarking
• SAQF compliance
  ○ Outcomes, levels, assessment, pathways
• Human-centered enablement
  ○ Role clarity and fair progression
• Delivery excellence
  ○ Structured PMO and acceptance criteria
• Sustainability
  ○ Toolkits, templates, and institutionalization
13

## Slide 14
Project Architecture
14

## Slide 15
System Components
• Governance and PMO
• Role and Competency Design Engine
• SAQF Qualification Authoring & Registration
• Training Delivery and Operations
• Partnerships and Provider Enablement
• M&E and Impact Measurement
• Incentives and Enablers Activation
• Knowledge Management and Archiving
15

## Slide 16
Data Flow and Integration
• Inputs
  ○ Program objectives, regulations, journey data
  ○ Stakeholder feedback, labor classification, SAQF
• Processing
  ○ Role analysis → competency mapping
  ○ Qualification blueprinting → provider onboarding
  ○ Enrollment → performance monitoring → incentives
• Outputs
  ○ JD cards, registered qualifications
  ○ Curricula, e-learning, trained workforce
  ○ M&E dashboards, incentive analytics, archives
16

## Slide 17
Technology Stack
• Project management: MS Project
• Collaboration & documentation
  ○ Secure repositories
  ○ Archiving compatible with Program systems
• Survey and analytics
  ○ Secure tools
  ○ Privacy-aligned data processing
• E-learning
  ○ SCORM/xAPI-compliant packages
  ○ Client LMS and archiving-ready
17

## Slide 18
Relevant Experience
18