## Slide 1
Guests of Allah Workforce Standards & Enablement
Prepared by Impetus Strategy Impetus Strategy

## Slide 2
Agenda
• Executive Summary
• Company Introduction
• Understanding of the RFP and Objectives
• Technical Approach and Methodology
• Project Architecture
• Work Plan, Timeline, and Milestones
2

## Slide 3
Agenda
• Project Team and Roles
• Quality Assurance and Risk Management
• KPIs and Service Levels
• Data Privacy, Security, and IP
• Compliance with RFP Requirements
• Deliverables Summary
3

## Slide 4
Agenda
• Assumptions
• Pricing Approach (Summary)
• Relevant Experience and Case Evidence
• Why Impetus Strategy
• Thank You
4

## Slide 5
Executive Summary
5

## Slide 6
Program overview
Impetus Strategy proposes a 30‑month program in Riyadh to define functional standards for 10 priority roles, register and SAQF‑level 10 qualifications, and upskill 1,000 practitioners through awareness, instructor‑led, and interactive e‑learning. Delivery mirrors a seven‑phase lifecycle with robust governance, quality assurance, risk management, weekly tracking, MS Project schedules, and reporting aligned to Ministry PMO templates.
6

## Slide 7
Company Introduction
7

## Slide 8
Who we are
Impetus Strategy is a management consulting firm specialized in social and economic development, impact strategy, public sector transformation, and non‑profit enablement. We operate across Riyadh, Jeddah, Makkah, Cairo, Dar es Salaam, Kuala Lumpur, and Jakarta, combining strategy, governance, data, and learning solutions to translate Vision 2030 priorities into operational programs.
8

## Slide 9
Core capabilities
• Strategy, governance, and ecosystem design for national programs and multi‑stakeholder coalitions
• Social and economic development, impact frameworks, and sustainability integration across portfolios
• Digital social development with data analytics, evidence generation, and insight‑driven decision support
• Stakeholder enablement and impact investment partnerships to scale service delivery and outcomes
9

## Slide 10
Understanding of the RFP and Objectives
10

## Slide 11
Objectives and expected outcomes
• Build functional standards and detailed job descriptions for 10 priority roles and register SAQF‑leveled qualifications
• Implement training pathways for 1,000 candidates with awareness, instructor‑led, and e‑learning delivery modes
• Define incentives and enablers to broaden non‑profit participation while institutionalizing monitoring and quality
• Achieve elevated service quality, transparent HR standards, better education alignment, and sustained capability transfer
11

## Slide 12
Technical Approach and Methodology
12

## Slide 13
Framework overview
• Evidence‑led job analysis anchored to service journeys and program objectives with benchmarking and triangulation
• SAQF‑compliant qualification design with explicit learning outcomes, assessment strategy, and progression pathways
• Multi‑modal learning pathways including awareness, instructor‑led sessions, and interactive e‑learning packages
• Incentives and enablers to catalyze sector participation with embedded QA, M&E, and risk management
13

## Slide 14
Methodological pillars
• Evidence and benchmarking: surveys, interviews, comparative references
• Standards‑driven design: SAQF alignment and occupation taxonomy mapping
• Learning science: competency outcomes and assessment‑for‑learning
• Governance and quality: gate reviews and change control
14

## Slide 15
Phased methodology
• Phases 1–2: Initiation and job analysis with charter, governance, risk and quality plans, workshops, surveys, journey mapping, and top 10 roles selection
• Phase 3: SAQF qualification design and levelling with purpose, outcomes, assessment, progression, stakeholder input, and formal registration
• Phase 4: Program execution for 1,000 candidates with provider selection, partnerships, contracting templates, governance, and M&E
• Phases 5–7: Incentives and enablers, monitoring and control with dashboards and QA, and closure with final acceptance and handover
15

## Slide 16
Project Architecture
16

## Slide 17
System components and integration
• Governance via Steering Committee, PMO templates, decision logs, and gate reviews aligned to Ministry standards
• Delivery engine with workstreams for job analysis, SAQF design, training, incentives, and M&E or QA
• Knowledge hub repository with version control for artifacts, curricula, evidence, and registered outputs
• Integration with Ministry systems for archiving and reporting with weekly status, quarterly and semi‑annual QA updates
17

## Slide 18
Work Plan, Timeline, and Milestones
18

## Slide 19
Project timeline by phase
19

## Slide 20
Project Phases & Timeline
Phase | Key Activities | Duration | Key Outputs
Phase | Key Activities | Duration | Key Outputs
Planning | Charter, governance, MS Project baseline, QA plan, risk register | 3 months | Inception and execution plan
Job Analysis | Stakeholder engagement, data collection, journey mapping, benchmarking | 6 months | 10 prioritized roles and job cards
SAQF Design | Qualification design, outcomes, assessment, registration submissions | 7 months | 10 SAQF‑registered qualifications
20

## Slide 21
Project Phases & Timeline
Phase | Key Activities | Duration | Key Outputs
Phase | Key Activities | Duration | Key Outputs
Execution | Provider partnerships, delivery to 1,000 candidates, periodic reports | 17 months | Training outputs and learning assets
Closure | Final report, acceptance letters, archival submission | 3 months | Handover and project closure
21

## Slide 22
Project Team and Roles
22

## Slide 23
Team Structure & Responsibilities
Position | Responsibilities | Experience | Time Allocation
Position | Responsibilities | Experience | Time Allocation
Managing Director | Executive sponsor, governance, stakeholder alignment, strategic decisions | 15+ years in consulting | 20%
EPMO Manager | PMO lead for schedule, scope, risk, reporting, and change control | 12+ years in PMO | 40%
Engagement Manager | Workstream leadership across job analysis, SAQF, training, incentives | 10+ years domain expertise | 50%
23

## Slide 24
Team Structure & Responsibilities
Position | Responsibilities | Experience | Time Allocation
Position | Responsibilities | Experience | Time Allocation
Technical & Educational Expert | Qualification design, learning science, assessment strategy and QA | 10+ years in L&D | 60%
Training Coordinator | Provider management, cohort logistics, delivery tracking and reporting | 7+ years in operations | 80%
24

## Slide 25
Quality Assurance and Risk Management
25

## Slide 26
QA, risk, and change control
• QA plan with acceptance criteria per deliverable, peer reviews, sign‑offs, version control, and semi‑annual QA reports
• Risk register with mitigations and contingencies, weekly reviews, and escalation thresholds to governance bodies
• Formal change control with impact analysis on scope, schedule, and cost, and approval routing through governance
• Compliance audits for classification, SAQF alignment, localization, safety, and data handling requirements
26

## Slide 27
KPIs and Service Levels
27

## Slide 28
Key Performance Indicators
KPI | Target | Measurement Method | Frequency
KPI | Target | Measurement Method | Frequency
Stakeholder Satisfaction | ≥90% | Survey and feedback forms | Monthly
Deliverable Quality Score | ≥95% | Quality review checklist | Per deliverable
Timeline Adherence | 100% | Milestone tracking and reporting | Weekly
28

## Slide 29
Key Performance Indicators
KPI | Target | Measurement Method | Frequency
KPI | Target | Measurement Method | Frequency
Data Accuracy Rate | ≥98% | Validation and verification checks | Continuous
Engagement Level | ≥85% | Workshop participation rate | Per session
29

## Slide 30
Success metrics targets
30

## Slide 31
Data Privacy, Security, and IP
31

## Slide 32
Privacy, security, and IP commitments
• Confidentiality with no disclosure of competition or client data without written approval and need‑to‑know access
• Use of client‑approved systems with secure storage, controlled transmission, and identity‑compliant archiving
• Intellectual property assigned to the government entity for public interest use as per RFP provisions
• E‑packages uploaded with open files and Arabic PDFs following required identity and formatting standards
32

## Slide 33
Compliance with RFP Requirements
33

## Slide 34
RFP compliance highlights
• Language and content approvals in Arabic with ≥10 working days pre‑workshop approval and identity‑compliant materials
• Localization adherence with junior roles staffed by Saudi nationals and dedicated female staff where required
• Submission via Etimad with separate technical and financial files and bank guarantees to the Vision Realization Office
• 30‑month duration with weekly monitoring, quarterly reporting, semi‑annual QA, and prescribed file formats
34

## Slide 35
Deliverables Summary
35

## Slide 36
Project Deliverables
Deliverable | Description | Timeline | Format
Deliverable | Description | Timeline | Format
Inception & Execution Plan | Project charter, governance, MS Project baseline, QA and risk plans | Month 3 | PDF Document
Role Standards & Job Cards | Prioritized role list and 10 job description cards with required fields | Month 7 | Report + Templates
SAQF‑Registered Qualifications | 10 qualifications with learning outcomes, assessment, and levelling | Month 12 | Submission Files + Certificates
36

## Slide 37
Project Deliverables
Deliverable | Description | Timeline | Format
Deliverable | Description | Timeline | Format
Learning Assets | 10 awareness, 10 training, and 10 interactive e‑learning packages | Month 26 | SCORM/e‑packages + Guides
Final Handover | Final project report, acceptance letters, e‑archiving submission | Month 30 | Bound Report + Presentation
37

## Slide 38
Assumptions
38

## Slide 39
Delivery assumptions
• Timely access to stakeholders and data sources with scheduled workshops and interviews coordinated in advance
• Review and approval cycles within 10 working days for content with aligned workshop scheduling dependencies
• SAQF registration follows standard procedures and timelines with early engagement and buffered schedules
• Provider contracts executed to meet delivery milestones and PMO templates provided at project kick‑off
39

## Slide 40
Pricing Approach (Summary)
40

## Slide 41
Payment Schedule
Phase | Milestone | Payment % | Timeline
Phase | Milestone | Payment % | Timeline
Phase 1 | Contract signing, mobilization, inception approval | 10% | Months 1–3
Phase 2 | Job analysis completed and 10 job cards approved | 15% | Months 2–7
Phase 3 | 10 qualifications designed, submitted, and SAQF‑leveled | 20% | Months 6–12
41

## Slide 42
Payment Schedule
Phase | Milestone | Payment % | Timeline
Phase | Milestone | Payment % | Timeline
Phase 4 | Cohorts launched, periodic delivery reports submitted | 35% | Months 10–26
Phase 5 | Incentives and enablers roadmap approved | 8% | Months 8–18
Phase 6 | Quarterly reports and semi‑annual QA accepted | 7% | Months 1–30
42

## Slide 43
Payment Schedule
Phase | Milestone | Payment % | Timeline
Phase | Milestone | Payment % | Timeline
Phase 7 | Final report and acceptance/closure letters | 5% | Months 28–30
43

## Slide 44
Budget allocation by phase
44

## Slide 45
Relevant Experience and Case Evidence
45

## Slide 46
Selected project credentials
• Social & Economic Surveys Priority Regions I and II: 6 and 12 months with +5M SAR and +10M SAR delivering multi‑source analytics
• Guests of Allah workforce standards enablement: 24 months, +9M SAR for role standards and enablement aligned to program objectives
46

## Slide 47
Selected project credentials
• Volunteers facilitation package for Guests of Allah: 36 months, +4M SAR with enablement models and benefits for volunteers
• Community needs assessment and capacity review: 12 months, +7M SAR with national rural diagnostics and institutional strengthening
• Visitor and resident experience measurement in Makkah with JLL: 3 months, +0.5M SAR and a 36‑month framework at +0.3M SAR
47

## Slide 48
Why Impetus Strategy
48

## Slide 49
Value proposition
• Aligned experience delivering functional standards in Guests of Allah
• End‑to‑end capability from job analysis to large‑scale training
• Proven governance with weekly tracking and semi‑annual QA
• Local presence with Arabic delivery and localization compliance
49

## Slide 50
Thank You
50

## Slide 51
Closing and next steps
Thank you for the opportunity to support Guests of Allah workforce enablement. We welcome discussion on scope, planning, and mobilization. For follow‑up, please reference the Etimad platform and RFP communication channels for official correspondence and clarifications.
51